## Slide 1
JP · TAP THAT BREWERY · PROPOSAL
Executing the
plan on a page.
Marketing strategy and execution. Twelve months.
v03 · 23 September 2026

## Slide 2
PART 01
Where you are.
The diagnosis, and what the catch-up settled.

## Slide 3
THE DIAGNOSIS
You do not have a strategy problem. You have an execution problem.
Three weeks on, that still holds. The refill business reached 96 to 113 active customers without a marketing push. Meta ads are working and there is nowhere to send the traffic. The website, POS and CRM do not talk to each other, so every campaign underperforms before it launches.
The constraint is hands, not ideas. We said that in August. Nothing since has changed it.

## Slide 4
WHERE YOU START FROM
Six numbers the plan runs on.
THE NUMBER | WHAT IT IS
96 to 113 | Active refill customers, reached with no marketing push
56% | Of them bought their system somewhere else and switched anyway
250 | Active refillers at six months. March 2027, or Christmas
1,000 | Active refillers by year three, across three regions
$2.55 vs $12+ | A schooner at home against a schooner at the pub
1 : 10 | One wholesale account is worth about ten households
A system that is not refilling is worth nothing. Every activity in this proposal is tested against the refiller number.

## Slide 5
SETTLED 18 SEPTEMBER · ONE OF THREE
The room is a destination, not a walk-in bar.
The Tap Room makes money on events and functions and loses it on walk-in trade. You settled that in principle: it is an events and local business venue. Your own words, that Oktoberfest is a sugar hit and you would take week-on-week revenue over it, are the clearest statement of strategy in three weeks of conversation.
What is left is whether the room reads as a showroom or an event space. That is your call inside 30 days, and everything here works under either.

## Slide 6
SETTLED 18 SEPTEMBER · TWO OF THREE
Home entertainment, not beer.
Every household deserves beer on tap is your line and it stays as the ambition. The brand idea underneath it is what the product does to an ordinary Saturday, which is turn a catch-up into the one people talk about.
That puts the kegerator beside the outdoor kitchen, the high-end barbecue and the coffee machine, rather than beside the bar fridge. It changes who will partner with you and what the hardware has to look like. Christy owns the wording.

## Slide 7
THE POSITION
Tap That is not in the beer business.
It is in home entertainment, and in the business of bringing people together. The product does not just put beer in a glass at home. It turns an ordinary get-together into an occasion worth hosting.
Every household deserves beer on tap stays as the ambition. It describes what you want to be true rather than why anyone buys. The brand idea sits underneath it, and it is the one that sells.

## Slide 8
THE POSITION · WHAT IT CHANGES
A design brief as much as a marketing one.
If the category is home entertainment, a keg system belongs beside the outdoor kitchen, the high-end barbecue and the coffee machine, rather than beside the bar fridge.
The systems on the market today read as appliances. Stand one next to a premium outdoor kitchen and it looks like equipment rather than something you chose. The comparison worth studying is the premium filtered-water tap: people pay for it because it looks right on the bench and they show it to visitors.

## Slide 9
THE POSITION · THE LINE
The best night in, on tap.
Chosen on 24 September from three drafts. It leans on occasion and hosting, which is the closest of the three to the idea underneath it and the easiest to build a campaign around.
The two it beat name arguments the work still has to carry: social proof and the be-the-envy-of-your-friends register, and the beer quality argument for the people who buy on taste. Christy works the line into key messaging inside 30 days.

## Slide 10
SETTLED 18 SEPTEMBER · THREE OF THREE
250 refillers is also the money number.
Break-even is about $50,000 a month against a current run rate of $35,000 to $45,000, and one month has already hit it. You confirmed that 250 active refillers clears it. The six-month number and the money number are the same number.
Which opens the one question this proposal cannot answer for you. Christy has put 250 by Christmas on the table given the outdoor entertaining season. March 2027 or Christmas 2026 should be settled before this is signed.

## Slide 11
PART 02
The work.
Seven workstreams, on your horizons.

## Slide 12
AT A GLANCE
Seven workstreams. The first carries the other six.
 | WORKSTREAM | THE MOVE
01 | Connect the system | Nothing compounds until the website, POS and CRM talk
02 | Switch existing owners | Your number one. They have already bought the hardware
03 | Referrals, JVPs, ambassadors | 18% of sales already, on a program nobody can hold
04 | The Tap Room as a destination | Events, functions and local business trade
05 | Wholesale as a function | Demand exists. Follow-up does not
06 | Brand, range and proof | Sharpened, not rebuilt. Proof you own and barely use
07 | Governance | Four numbers, one page, one rhythm
Horizons are your own: 30 days to mid-October, three months to mid-December, six months to March 2027, one year to September 2027.

## Slide 13
WORKSTREAM 01
Connect the system.
Spending more on ads before this is fixed buys traffic the business cannot catch.
ACTIVITY | WHAT WE DELIVER | WHEN
Website upgrade | A CMS you run yourself, wired to GoTab, Fishbowl, the Pixel and the CRM. Integrations proven before launch, not promised | 3 months
SEM | Search on the category nobody on the Gold Coast owns: beer at home, keg refills, keg systems | 3 months
GoTab and Fishbowl | Every sale writes back to the customer record. We ready the CRM and the site so nothing is built twice | 3 months
Trigger-based CRM | Consumption-timed reminders replace the blanket 90-day SMS. Four segments, one re-engagement flow | 3 months
Meta Ads split | Switcher, giveaway, destination and retargeting, with a landing page for each rather than a home page for all | 30 days
One monthly report | Four numbers on one page. Active refiller defined once, before the first report | 30 days

## Slide 14
WORKSTREAM 02
Switch the owners who already have a system.
The lead priority. They have bought the hardware and overcome every objection already.
ACTIVITY | WHAT WE DELIVER | WHEN
National retail, to explore | Harvey Norman, JB Hi-Fi and The Good Guys. A gift-with-purchase or first keg free at franchisee level, plus the buyer database | 3 months
Kegland and Benchy | Buy or partner for the owner databases. A refill voucher in the box | 3 months
Switcher campaign | The lead priority. One offer, one page: you already have the hardware, we are the beer, first keg on us | 3 months
Switcher offer conditions | Compatibility check, one offer per household or venue, proof of ownership, liquor promotion wording, Meta targeting 18 and over | 3 months
Lease-to-buy and delivery | Your launch items. Offer page, CRM flow and launch creative for both | 3 months
Outdoor kitchen specification | A keg-and-tap unit as a standard inclusion. Visuals and a demand test before anything is manufactured | 6 months

## Slide 15
WORKSTREAM 03
Referrals, JVPs and ambassadors.
ACTIVITY | WHAT WE DELIVER | WHEN
Referral program | Tokens do not travel. A free keg does. Rebuilt around a keg and a QR card an owner hands to a mate | 3 months
Internal referral program | The same mechanic pointed at system sales, for the team and existing customers. Tracked so it can be paid | 3 months
JVPs and partners | The list, offer, outreach and follow-up from the CRM. Mark's venues, Never Quit and the tour operators | 3 months
Trades as a referral force | Plumbers and kitchen installers carry the same card, with a kickback the CRM tracks | 3 months
Influencer strategy and outreach | Three tiers: local reach, outdoor living, food and drink. Gifted first, paid where earned, to ABAC rules. Plan: tapthat-creator-plan.pages.dev | 3 months
UGC and ambassadors | Kurt, Troy, Mitch, Aden and Ash. The brief, the shoot plan, the release schedule, the rights | 3 months
Hosted tasting nights, to test | A test. An owner hosts at home and earns a keg or credit on anything sold | 6 months
Service networks, to explore | East coast technician routes already visiting thousands of businesses. A referral on a service call | 6 months

## Slide 16
WORKSTREAM 04
The Tap Room as a destination.
ACTIVITY | WHAT WE DELIVER | WHEN
Competitions, twice a year | About thirty systems each. The insider offer lands the moment someone enters | 3 months
Local business program | Lunch and after-work trade from the industrial area: offer, outreach list, collateral | 3 months
Tours and tastings | Onto the circuit. The award and the bus parking are the reasons to stop here | 3 months
Weddings and functions | Hens and bucks through to reception supply. Mark's roughly 300 weddings a year | 6 months
Party rental | A system in a house for a weekend is a demo the host runs. A keg guarantee replaces the $75 barrier | 6 months
Membership redesign | Held at your request until you release it. One program for the refill business, not two. Two posters quote different prices | On hold

## Slide 17
WORKSTREAM 05
Wholesale as a function.
Bars have approached you and it has not converted. That is not a demand problem.
ACTIVITY | WHAT WE DELIVER | WHEN
Structure and KPIs | Targets, pipeline stages and reporting in the CRM, so the function exists before the person does. A brief for the next hire | 3 months
Venue outreach | Event venues, niched venues and sporting clubs: the list, the offer, the twelve-touch sequence, run from the CRM | 3 months
Club and venue offers | Club-branded kegs, season minimum guarantees, and rigs that move from footy to cricket | 6 months

## Slide 18
WORKSTREAM 06
Brand, range and proof.
Not rebuilt. Sharpened around one enemy, overpriced pubs, and your own line.
ACTIVITY | WHAT WE DELIVER | WHEN
Where the category sits | Settled: the best night in, on tap. Christy works it into key messaging and into every brief | 30 days
Key messaging by market | One page per segment: what we say, what we prove, what we ask | 30 days
Customer journey mapped | First contact to first refill to reorder, with the CRM trigger at each step | 30 days
Proof assets | The Crafted award, the reviews, no CO2, and the integrated units already selling and nowhere on the site | 3 months
Range and heroes | Social proof at the point of sale: most popular, award winner, what to eat with it | 6 months
Campaign artwork | The switcher, the referral program, the ambassador and creator content, and the competition campaign | Ongoing

## Slide 19
WORKSTREAM 07
Governance.
Agreed on 18 September. Ronnie locks the standing day.
ACTIVITY | WHAT WE DELIVER | WHEN
Meeting rhythm | A weekly 45 minutes with Harry and Justin, led by Christy. A monthly hour with both founders against the four numbers | 30 days
Who does what | The responsibility matrix, agreed and dated. It stays a draft until you and Chris return the split | 30 days
Reviews on your ladder | Mid-October, mid-December, March 2027, September 2027. Every review asks first whether active refillers moved | As dated

## Slide 20
BEYOND THIS ENGAGEMENT
Two of these are briefs, not the work itself.
Designing for her, and the unit as an object worth owning. Acting on either is product and industrial design, with different people in it and a different order of spend.
Both are scoped separately in the Product Design Brief, at /product-design-brief. They are concepts at this stage, not work booked into a horizon, which is why neither carries a date in the workstreams.
The decision it needs first is whether Tap That makes hardware, specifies it with a manufacturer, or licences the design.

## Slide 21
PART 03
How it runs.
The first sprint, the ladder, and what we need from you.

## Slide 22
THE FIRST 30 DAYS
Your own 30-day list is the first sprint.
 | WHAT CLOSES
01 | The shape decision, finished. Showroom or event space
02 | Residential versus commercial. Where the energy goes
03 | Key messaging and the customer journey. Delivered by us, signed by you
04 | KPIs and the meeting rhythm. Four numbers, one definition of active refiller
05 | The Jewell split. What we own, what Harry and Justin keep
06 | Ambassadors named and briefed, with a shoot date in the calendar
07 | Settle $2.55 as the per-schooner figure on the live ad
08 | The 250 date. March 2027 or Christmas 2026
We work it with you rather than around you.

## Slide 23
WAYS OF WORKING
Who does what, and how often.
 | HOW IT RUNS
Christy runs it | Christy Kilmartin leads the engagement: strategy, direction, and the call on what gets built next. Your first call on anything
Harry executes | Harry is the operator inside Tap That. Everything we design is built to be run from that seat
Weekly | Forty-five minutes with Harry and Justin, led by Christy. Ronnie locks the standing day
Monthly | One hour with both founders on the four numbers. Decisions taken in the room and recorded
Reviews | Mid-October, mid-December, March, September. A written review and a stop-or-continue conversation at each
Sign-off | One named person approves messaging, offers and anything that goes to market. We suggest Justin, with Chris consulted on brand and product

## Slide 24
WHAT WE NEED FROM YOU
Seven inputs, and when.
INPUT | WHY, AND WHEN
Showroom or event space | The last piece of the shape decision. Within 30 days
The 250 date | March 2027 or Christmas 2026. It changes the shape of the first three months. Before this is signed
The Jewell split | Your mark-up of the workstreams: what we own, what Harry and Justin keep. At the first weekly check-in
One definition of active refiller | Before the first monthly report, or the number gets argued about instead of acted on
$2.55 as the per-schooner figure | Confirmed on the live ad, and the other maths retired. Within 30 days
GoTab and Fishbowl timeline | It sequences the CRM build. Before the three-month sprint starts
Introductions | The ambassadors, Mark's venues, and the Kegland and Benchy contacts

## Slide 25
PART 04
Investment.
Two options, one plan, one rhythm.

## Slide 26
OPTION A
The ninety-day sprint.
Discover and Design already delivered, rack value $20,000, charged at $4,995 on acceptance of either option.
LINE | FEE
Foundation builds. Website rebuild with the buy path and proof pages, SEM set-up, trigger-based CRM with segments, three campaign landing pages | $9,250
Program design. Switcher offer and partner approach, referral program, wholesale structure and hire brief, key messaging and the customer journey, the competition campaign | $8,500
Running the sprint, three months. SEM and Meta management, JVP and wholesale outreach, content and artwork, the rhythm and the report | $3,250 a month, $9,750
Option A total | $25,000 + GST normally $27,500
$25,000 on acceptance, or $8,333 a month across the three months. Stop or continue at the mid-December review. The line fees are the standard rate and sum to $27,500; the discount is applied to the total.

## Slide 27
OPTION B
Twelve months.
An active refill customer is worth about $2,400 a year. Option B pays for itself at twenty-five additional refillers held for a year, and your own six-month target adds about 145.
LINE | FEE
Everything in Option A, delivered in the first three months | Included
Months four to twelve. Weddings and functions, party rental reworked, the membership redesign when you release it, range and hero marketing, club and venue offers, SEM, outreach, content and artwork continuing, the reviews at March and September | Included
Option B total | $4,999 a month + GST normally $5,500 $59,988 over twelve months
Monthly in advance. Minimum three months, then stop at any review with a month's notice.

## Slide 28
NOT INCLUDED
What sits outside the fee.
ITEM | HOW IT IS HANDLED
Media spend | Billed directly by Meta and Google. Management of spend above $5,000 a month at 10% of the excess
Photography and video | $1,250 a day, quoted per shoot
The Urban Legends booking widget | Scoped separately once the operator agrees to carry it
Third-party software and print | GoTab, Fishbowl, any booking tool licence, and print runs
All figures are Australian dollars, exclude GST, and include project management and administration.

## Slide 29
DECISION · PROPOSAL V03
Four decisions, and we start.
We propose the week of 12 October, which closes the 30-day sprint before the middle of November.
01
Which option, A or B.
02
Who signs for Tap That Brewery.
03
The 250 date: March 2027, or Christmas 2026.
04
A start date.
Accepted for Tap That Brewery:
For Jewell Projects: Clent Jewell

## Slide 30
Next.
Signed proposal back, and the first weekly check-in booked.
Christy Kilmartin leads it · Clent Jewell · clent@jewellprojects.com